RS-D620 Power Sequencer

Proof of Concept — Technical Concept Document

| Field | Value |
| --- | --- |
| Project | RA6M5-based multi-rail power sequencer, proof of concept |
| Prepared by | MXT Creation S.R.L. |
| Date | 19 August 2026 |
| Status | Revision 2 — incorporating Renesas review comments of 20 August 2026 |
| Development completion | End of September 2026 |
| Demonstration | October 2026; schedule to be coordinated by Renesas |
| Audience | AI accelerator developers |

# 1. Purpose

This revision incorporates the review comments received from Renesas on 20 August 2026. Section 12 lists each comment and where it has been addressed.

This document defines the scope, architecture and demonstration plan for the RS-D620 proof of concept, agreed in the clarification meeting. It correlates the requirements received from Renesas with the technical approach MXT proposes, records the design decisions taken and lists the items still open.

The POC demonstrates that an MCU-based power sequencer with a Windows configuration and reporting application is a viable alternative to a fixed-function sequencer such as the UCD91320. It is not a product prototype: it runs on evaluation kits with emulated rails.

# 2. Requirements traceability

## 2.1 From the clarification meeting

| # | Requirement | How the POC addresses it |
| --- | --- | --- |
| M1 | Two RA6M5 kits connected in cascade | 2 × EK-RA6M5 with a defined inter-board signal set (§4.2) |
| M2 | Reset and fault signals between boards | FAULT# wired-OR bus and a common RESET line (§4.2) |
| M3 | Programmable over USB-to-UART | Each board presents a USB-CDC serial interface on the MCU USB port; the PC application opens both ports. The EK-RA6M5 on-board debug interface does not provide a VCOM port, so USB-CDC on the MCU is used instead |
| M4 | Emulated supplies | Potentiometer board feeding the monitored ADC inputs, representing rail output voltages |
| M5 | Enable outputs observable | EN pins routed to LEDs and reported to the application as part of live telemetry |
| M6 | Sequencing configurable from the PC application | Configuration-driven firmware: the application generates a configuration image that the firmware interprets (§5.1) |
| M7 | Fault reading — ADC monitoring of UV and OV | Per-rail OV/UV thresholds, fault detection, configurable fault response, event log readable from the application (§5.3) |

## 2.2 From the MRD POC section

| # | MRD requirement | Coverage |
| --- | --- | --- |
| P1 | Windows application design and usability | Primary POC deliverable; project-file based, with offline mode |
| P2 | How the sequence is configured | Rail configuration screens with dependencies, delays and thresholds |
| P3 | "If / then" logic configurable via GUI | Condition builder: source, operator, threshold, action — serialised into the configuration image |
| P4 | Timeout option | Per-rail sequence-on and sequence-off timeout with configurable action |
| P5 | Mechanism to read faults | Event log with timestamps, readable and clearable from the application |
| P6 | Cascaded environment appears as a single sequencer | System-level project file, continuous rail numbering across boards, cross-board dependencies, merged event log (§6) |

Note on scope change. The earlier written guidance stated that cascading could be omitted from the POC. The clarification meeting overrides this, and Renesas has confirmed in review that two cascaded boards plus a Windows application showing the cascaded sequence are required.

## 2.3 Explicitly out of POC scope

Deferred to the product phase, as agreed: margining, current monitoring, temperature monitoring, PMBus, black box fault log, watchdog and system reset outputs, SEU mitigation, dual-bank configuration update, boot time optimisation, full rail count, and cascading beyond two devices.

# 3. Assumptions and confirmations

- 8 emulated rails per board, 16 across the system. Confirmed by Renesas in review.

- Two engineers available, one on firmware and one on the PC application.

- Evaluation kits available from stock. Distributor stock has been confirmed for the eight kits required (RTK7EKA6M5S00001BE), so procurement is not on the critical path.

- Two emulation boards, one per kit, hand-wired on prototype board rather than designed PCBs. Whether a fabricated PCB fits the schedule is to be defined.

- Four demonstration sets. Two retained at MXT and two shipped to Renesas in the United States. Each set comprises two EK-RA6M5 kits and two emulation boards, so eight kits and eight emulation boards in total. The two sets held at MXT give the firmware engineer and the application engineer each a complete cascaded rig, which removes a hardware dependency between them during integration and leave one set available for support after the others are dispatched. Hardware is quoted separately from the development effort (§9).

# 4. Hardware topology

## 4.1 Overview

Figure 1 — POC hardware topology

## 4.2 Inter-board signals

| Signal | Type | Function |
| --- | --- | --- |
| CONTROL | Wired-OR, open-drain, 10 kΩ pull-up | System start and ordered stop. Asserted by the front-panel switch or driven by the master board on command from the application. Active-low, polarity configurable. |
| FAULT# | Bidirectional wired-OR, 10 kΩ pull-up | Input while idle. A board detecting a fault drives it low, informing the other board. Independent of the PC and of CONTROL. |
| A_DONE | Board 0 output → board 1 input | Serial cascade only. Sequence-on dependency: board 1 does not start until board 0 reports all rails good. Not used in parallel cascade. |
| B_OFF | Board 1 output → board 0 input | Serial cascade only. Sequence-off dependency: board 0 does not shut down until board 1 has. Not used in parallel cascade. |
| RESET | Common line | Synchronises the time base across cascaded boards, so programmed delays and log timestamps remain consistent. Also used to demonstrate unplanned-reset behaviour (§7). |
| GND | — | Mandatory common reference. |

A separate SYNC_CLK line is not required. Renesas has confirmed that the common RESET line is used to synchronise the time base of the cascaded boards.

Where serial cascade is used, two handover wires are needed rather than one: A_DONE for power-up ordering and B_OFF for power-down ordering. Without B_OFF, ordered shutdown across the system cannot be demonstrated.

## 4.3 Cascade modes

The POC supports two cascade modes. The mode is selected in the Windows application and written into the configuration image of both boards; it is not a wiring change.

Parallel cascade — the mode the customer requested. Both boards start their sequence when the system start signal is asserted, and both shut down when it is de-asserted. Rails on both boards come up, and come down, in parallel according to their individually configured delays. No handover signals are involved: CONTROL alone coordinates the boards, and the common RESET line keeps their time bases aligned so that a delay configured on board 1 means the same as the same delay on board 0.

Serial cascade. The boards sequence one after the other. Board 1 does not begin until board 0 signals that all its rails are good, over A_DONE; on shutdown, board 0 waits for B_OFF from board 1, giving reverse order across the system. This mode requires the handover signals to be wired, and requires synchronisation between the boards; parallel cascade does not.

The application validates that both boards carry the same cascade mode, and that the signals a serial configuration depends on are declared as present.

## 4.4 Rail emulation

Each kit has its own emulation board. Each monitored input is driven by a potentiometer between 3.3 V and ground, representing a rail output voltage. Turning a potentiometer past a configured threshold produces an OV or UV fault, which is the primary fault-injection mechanism for the demonstration.

CONTROL and RESET are single switches wired to both kits, not one switch per board.

Both emulation boards share one design, with the switch section populated on one board only. If the boards are fabricated rather than hand-wired, this keeps a single layout and a single bill of materials, with a depopulation variant for the second board. The pull-up resistor belongs to the switch section so that it is depopulated with it, otherwise the two boards present parallel pull-ups on the common lines.

Divider impedance constraint. The RA6M5 ADC12 specifies a maximum permissible signal source impedance of 1 kΩ. Potentiometer value and any series resistance must respect this, otherwise the specified conversion times and accuracy do not apply.

## 4.5 Enable outputs

Enable pins must be held inactive from power-on. Between reset release and the first instruction that configures the port registers, RA6M5 GPIOs are high impedance; software cannot guarantee the state during that window. An external pull-down on every EN pin is a hardware requirement. The same applies to the UCD91320, whose I/O pins are held high-impedance throughout its initialisation routine, so this is not specific to an MCU-based solution.

# 5. Firmware architecture

## 5.1 Configuration-driven design

The firmware contains no hard-coded sequence. The application generates a binary configuration image which the firmware validates and interprets:

- Header: format version, device role, CRC

- One fixed-size record per rail: EN pin, ADC channel, turn-on delay, turn-off delay, OV and UV thresholds, dependency mask, timeout and timeout action, fault action

- Condition records for the "if / then" logic

Fixed-size records and a table interpreter — no parser, no scripting engine. Following the Renesas review, the interpreter is implemented as a data-driven state machine: rail states and transitions are held in tables and driven by the configuration image, rather than encoded in control flow. This keeps timing behaviour uniform across rails and makes the engine extensible to the full rail count without restructuring. It is also what makes the demonstration meaningful: the sequence changes from the GUI without recompiling or reflashing.

The image is stored in data flash using background operation, so it survives a power cycle and the device operates standalone once configured.

## 5.2 Monitoring

ADC12 in continuous scan mode, with results transferred by DTC. At the end-of-scan event, the scan-complete interrupt checks each channel result against its configured OV and UV thresholds.

This approach was adopted on the recommendation of the Renesas review. The ADC12 window compare function can only cover one channel at a time unless the Window A and Window B limits are rewritten before each conversion completes, which is impractical across sixteen rails. End-of-scan checking avoids that constraint and keeps the per-rail thresholds independent. Window compare remains available for a small number of critical rails should a hardware-speed path be required later.

Measured scan performance will be reported as a POC result rather than predicted.

## 5.3 Fault handling

Detected in the POC: over-voltage, under-voltage, sequence-on timeout, sequence-off timeout, and fault asserted by the other board.

Configurable responses: log only; shut down the affected rail; shut down the whole system in reverse sequence order; assert FAULT# to the other board.

Events are logged with a timestamp and are readable and clearable from the application.

## 5.4 Start and stop synchronisation

Two commands sent sequentially over two serial ports arrive 1–10 ms apart, which is not deterministic and exceeds the system shutdown budget. The POC therefore separates arming from triggering:

- The application arms each board individually and confirms both are armed.

- The application commands the master board, which drives the CONTROL line.

- Both boards observe the same edge and begin sequencing within microseconds.

The same code path serves both the hardware switch and the application command. At the product stage, "arm" becomes a PMBus OPERATION command while CONTROL remains the same hardware pin, so no sequencing logic changes.

In parallel cascade, this is all that is required: both boards see the same CONTROL edge and run their own sequences concurrently. In serial cascade, CONTROL starts board 0 only, and board 1 waits on A_DONE.

Each board samples CONTROL by level, not edge, on leaving initialisation, so a system powered up with the switch already asserted starts correctly.

## 5.5 Device identity and role

The address is read from GPIO strapping at boot and identifies the board on the communication link. The cascade role — which board leads in serial cascade — is separate from the address and is set in the configuration image. In parallel cascade the role has no effect on sequencing. Both values are reported to the application, which validates that addresses are unique and that the roles are consistent with the selected cascade mode.

# 6. PC application architecture

## 6.1 Structure

A layered design, with a device and protocol API separated from the user interface. The API layer owns the transport, the command set and the device model; the user interface is one consumer of it. Separating the two at the outset means a production programming utility and scripted test automation can be built on the same layer later, without reworking the application.

Proposed platform: C# on .NET. The runtime is MIT-licensed with no redistribution restriction, the team has existing C# experience, and a self-contained build runs without the user installing a separate runtime first. Final selection to be confirmed against team experience.

## 6.2 System model

The project file describes a system, not a device:

Project {

devices: [

{ address, role, railOffset, rails[...] },

{ address, role, railOffset, rails[...] }

],

interBoardSignals: { ... }

}

Continuous rail numbering across the system is produced by applying each device's rail offset. Each board knows only its local rails; the system-level view exists in the application.

The device abstraction is address-based from the outset, so replacing two serial ports with a single PMBus carrying two addresses changes only the transport layer.

## 6.3 Cross-board dependencies

When the user specifies that a rail on board 1 depends on a rail on board 0, the application compiles this into hardware terms: an output condition on board 0, and a corresponding input dependency on board 1. The user expresses intent; the application allocates the signals.

Expressing a cross-board dependency as a single statement, rather than requiring the user to allocate a general-purpose output on one device and configure a matching input dependency on the other, is a deliberate usability decision. Usability is the primary POC evaluation criterion.

The application validates that the inter-board signals a configuration requires are declared as present.

## 6.4 Screens

- Device discovery and project assembly, including selection of the cascade mode (parallel or serial)

- Rail configuration: pin assignment, delays, thresholds, dependencies, timeout actions

- Condition builder for "if / then" logic

- Live monitor: measured voltages, EN states, rail states, system state

- Event log, merged across boards and ordered by timestamp

- Project file save and load, with offline editing

## 6.5 Protocol

A binary protocol carried over USB-CDC, shaped along PMBus lines: command codes, page semantics for rail selection, block read and write structure. PMBus itself is out of POC scope, but adopting its shape now means the command set, data model and application survive the transition to a PMBus transport.

Telemetry is obtained by polling from the application, not pushed by the board. A PMBus target cannot initiate transfers; building the monitor on a push model now would require rewriting it later.

## 6.6 Distribution and code signing

The POC application will not be code-signed. Obtaining an organisation-validated code signing certificate requires company validation before issuance, and the recurring cost belongs to the product phase rather than to a proof of concept.

The consequences should be understood in advance:

- On a standard Windows machine, SmartScreen displays a warning for an unsigned executable. The user can proceed, but the warning is visible.

- On a managed corporate machine with application control policies in force — WDAC, AppLocker or Smart App Control — an unsigned executable may be blocked outright, with no user-accessible override. Endpoint protection software may additionally quarantine the binary.

- Whether the application can be installed therefore depends on the IT security policy of the machine, not on the application itself.

Mitigation for the demonstration: the application runs on a standard Windows laptop under our control, so the demonstration itself is unaffected. The application will also be delivered as a self-contained folder that runs without an installer, which avoids installation-time restrictions on some, though not all, managed machines.

If Renesas engineers need to run the application on their own machines before the demonstration, this should be raised early so their IT policy can be checked, or so a signed build can be arranged.

For the product phase, code signing is required. Since Renesas would distribute the application to its customers, the signing identity should most likely be Renesas rather than MXT; this is listed as an open item.

# 7. Demonstration scenarios

| # | Scenario | What it demonstrates |
| --- | --- | --- |
| S1 | Configure and download | A sequence spanning both boards is created in the application, downloaded, and stored. The boards are power-cycled and retain the configuration. |
| S2 | Power-up, parallel cascade | CONTROL is asserted. Both boards start together and all 16 rails come up in parallel according to their individually configured delays. The application shows a single timeline across all 16 rails. This is the mode the customer requested. |
| S3 | Power-down, parallel cascade | CONTROL is de-asserted. Both boards shut down together, all 16 rails coming down in parallel according to their configured delays. |
| S3b | Serial cascade | The cascade mode is changed to serial in the application and downloaded, with no rewiring. On power-up, rails 1–8 come up on board 0, board 0 asserts A_DONE, and rails 9–16 follow on board 1. On power-down the order reverses via B_OFF. Demonstrates that the mode is a configuration choice. |
| S4 | Fault and coordinated shutdown | A potentiometer on board 1 is turned past the OV threshold. Board 1 detects the fault, drives FAULT# low, and board 0 shuts its rails down in reverse order. The application shows one merged log identifying the board 1 rail as the first fault. |
| S5 | Timeout | A rail is prevented from reaching its threshold. The sequence-on timeout expires and the configured action is taken and logged. |
| S6 | Unplanned reset | RESET is asserted while the system is running. All enable outputs fall to their pull-downs immediately, with no ordered shutdown. Included deliberately: it illustrates a behaviour common to any reset source — watchdog, brownout, or an uncorrectable memory error — and opens the discussion of what the product should do in that case. |

# 8. Technical findings from RA6M5 evaluation

Verified against the RA6M5 User's Manual (R01UH0891 Rev.1.50) and relevant for the product architecture:

- The RA6M5 has no analog comparator. An ACMPHS-based fast fault path, referred to in the MRD, is not implementable on this device.

- POEG acts only on GPT output pins, and offers four groups. It is not suitable for controlling general-purpose enable outputs, and its trigger source cannot be changed after being set once.

- The correct mechanism is the ELC port group function. Ports 1 to 4 are linked to the Event Link Controller; on an event, a mask register clears selected output bits with no CPU involvement. This works on any GPIO, covers up to 64 pins, and is reconfigurable at run time.

- ADC channels are not equal. Sixteen channels are specified at ±4.5 LSB absolute accuracy; thirteen channels on unit 1 are specified at ±7.5 LSB. Critical rails should be allocated to the higher-precision group. An external precision reference on VREFH0 and VREFH is required for these figures to apply.

- ADC12 window compare covers one channel at a time unless the Window A and Window B limits are rewritten before each conversion completes. Confirmed by the Renesas review; end-of-scan checking is used instead (§5.2).

- Maximum permissible source impedance is 1 kΩ, which constrains monitoring divider design and its power budget.

- Certain channel combinations on the two ADC units may not be selected simultaneously, which may reduce the usable analog channel count below 26. To be confirmed with Renesas, as it affects the 22 versus 26 rail decision.

# 9. Effort estimation

| Stream | Effort |
| --- | --- |
| Firmware | 21 MD |
| PC application | 21 MD |
| Protocol definition and emulation board | 6 MD |
| Integration across two boards | 9 MD |
| Setup and operating guide | 2 MD |
| Walk-through | 1 MD |
| Total | 60 MD |

The figures cover the complete software development, the setup and operating guide, and the demonstration walk-through. They are independent of the number of demonstration sets built.

## Hardware

Hardware is additional to the software development effort above and is quoted separately. Four sets are required: two retained at MXT, two shipped to Renesas in the United States.

| Item | Per set | Total, 4 sets |
| --- | --- | --- |
| EK-RA6M5 evaluation kit | 2 | 8 |
| Emulation board | 2 | 8 |
| Inter-board harness, USB cables, packaging | 1 | 4 |
| Assembly and test | — | Included in the per-set price |

The two emulation boards in each set share one design, with the CONTROL and RESET switch section populated on one board only (§4.4). Each set is assembled and fully tested at MXT before dispatch. A price is provided with the quotation.

Renesas acts as importer of record in the United States and covers customs duties and any import charges. MXT purchases the hardware, assembles and tests each set, and dispatches to the address Renesas provides; shipping cost is invoiced at cost. Dispatch should allow at least one week of transit and clearance ahead of any demonstration date.

## Scope reduction candidates

The plan carries limited contingency. Should the schedule come under pressure, the following would be dropped, in this order. Agreeing the order now means the decision is a planned one rather than one taken under pressure in the final week, and none of these affects the six POC objectives in section 2.

- Serial cascade mode. The customer requested parallel cascade, and that is what scenarios S2 and S3 demonstrate. Serial cascade is included to show that the mode is a configuration choice rather than a wiring change, but it is not a stated requirement for the POC. Dropping it removes scenario S3b, the mode selector and its cross-board validation in the application, and the external-dependency states in the sequencing engine. The A_DONE and B_OFF lines would still be wired, so the mode can be added later without hardware change. Approximately 3 to 4 MD.

- System-level view in the application. The two boards would be presented as two devices rather than as one continuously numbered system. The demonstration still works; it is less convincing against P6. Approximately 3 MD.

- Configuration persistence in data flash. The configuration would be held in RAM only and re-sent from the application after each power cycle. Visible in scenario S1, but acceptable if explained. Approximately 2 MD.

# 10. Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Protocol not frozen early | The two engineers block each other from week 4 | Freeze in the first three days; it requires no hardware |
| No schedule contingency | Any setback moves the development completion date | Reduction candidates listed in §9, in the order they would be dropped, for agreement with Renesas in advance |
| Engineer availability | The plan assumes two engineers for the full duration | To be confirmed before the date is committed |
| Requirements still moving | Rework | This document to be confirmed by Renesas before development starts |
| Unsigned application blocked by IT policy on a shipped set | The set cannot be used at the receiving site | Renesas selects one of three routes before dispatch; a dedicated laptop outside the domain is the simplest (§6.6) |
| Shipping and customs delay | A set arrives after the intended demonstration date | Dispatch with at least one week of margin; Renesas is importer of record and clears customs |

# 11. Open items

## Resolved in the Renesas review of 20 August

- Rail count: 8 per board, 16 cascaded — confirmed.

- Two cascaded boards and a Windows application showing the cascaded sequence — confirmed as required.

- Timing: development completion end of September, demonstration in October, schedule coordinated by Renesas. Audience is AI accelerator developers; the specific customer is not disclosed.

- SYNC_CLK is not required; the common RESET line synchronises the cascaded boards.

## Blocking

- Which of the three routes in §6.6 applies at each receiving site — dedicated laptop, allowlisted machine, or code-signed build. Needed before dispatch.

- Confirmation of engineer availability for the full duration.

## To be resolved during the POC, affecting the product

- Margining approach, given the customer's rejection of PWM-based margining.

- Analog channel budget: 26 channels cannot serve voltage plus current for 22 to 26 rails. External ADC, analog multiplexer, or PMBus telemetry from digital point-of-load regulators.

- Package selection. The 176-pin BGA is 13 × 13 mm at 0.8 mm pitch but is offered only at −40 to +85 °C; the 176-pin LQFP offers −40 to +105 °C but is 24 × 24 mm at 0.5 mm pitch. No option provides pitch, size and extended temperature together.

- Accuracy target for OV and UV thresholds, and whether per-channel production calibration is acceptable.

- Required behaviour on an unplanned reset (§7, S6).

- A latency figure for the digital critical fault path. "Extremely low" is not specifiable.

- Ownership and maintenance of the configuration application.

- Code signing identity for the product-phase application, and who holds the certificate.

# 12. Review comments incorporated

Comments received from Renesas on 20 August 2026 and where each is addressed.

| From | Comment | Addressed in |
| --- | --- | --- |
| Takuya | Development completion end of September; demonstration likely October | Title block, §11 |
| Takuya | Two cascaded boards and a Windows application showing the cascaded sequence are required | §2.2, §11 |
| Takuya | 8 rails per board, 16 cascaded, is acceptable | §3, §11 |
| Takuya | Can several demonstration sets be built, with one or two shipped to the US? | §3, §6.6, §9, §11 |
| Takuya | Demonstration to AI accelerator developers; specific customer not disclosed | Title block, §11 |
| Gary | The EK-RA6M5 on-board debug does not provide VCOM; USB-CDC on the MCU USB port must be used | §2.1 M3, §4.1, §6.5 |
| Gary | A_DONE and B_OFF are used only in serial cascade; in parallel cascade both boards start on system start | §4.2, §4.3, §5.4, §7 |
| Gary | SYNC_CLK is not required; RESET synchronises the cascaded boards | §4.2, §5.5 |
| Gary | A data-driven state machine should be used for the table interpreter | §5.1 |
| Gary | Window compare covers one channel unless limits are rewritten each conversion; use continuous scan with end-of-scan checking | §5.2, §8 |
| Gary | Rails on both boards come up and down in parallel with their specified delays, as the customer requested | §4.3, §7 S2 and S3 |